## Clean
Priority | Feature Category | Feature | Assigned Date | Due Date | Completion Date | Assigned To | Decription
1 | Game World | Game World exists | No Record | 2020-02-13 | 2020-02-13 | Eli | A world that the player can view/interact with
2 |  | Physics | No Record | 2020-02-27 | 2020-02-27 | Eli | gravity, drag, and collision (momentum / weight?)
6 |  | Terrain Texture | No Record | 2020-02-13 | 2020-06-10 | Alex | terrain texturing, litteraly just a circle race track png
3 | Player / Interaction | Driving | No Record | 2020-02-27 | 2020-02-27 | Eli | acceleration curve
5 |  | Pause Menu | 2020-06-10 | 2020-06-17 | 2020-06-17 | Mohammed | interaction menu that the player triggers to stop car input in game
4 |  | Start Menu | 2020-06-05 | 2020-06-10 | 2020-06-09 | Parker | Basic menu for the player to start the game
8.1 |  | Background music (radio) | No Record | 2020-05-25 | 2020-06-16 | Eli & Sumedh | déjà vu
3.1 | Car Controls | Acceleration | 2020-02-27 | 2020-06-05 | 2020-06-04 | Eli | the rate at which the car increases speed to match the maximum
3.2 |  | Steering | 2020-02-27 | 2020-06-06 | 2020-06-06 | Eli | car turns while moving forward ¦ A - turn left / D - turn right
3.3 |  | Boost | 2020-05-29 | 2020-06-05 | Pending | Kunal | a button pressed to temporarily increase speed
7.2 | Start Menu | Title Image | 2020-06-10 | 2020-06-18 | 2020-06-17 | Alex | Image with the title of "Space Racer" and maybe icon if Alex is feeling charitable
7.1 |  | Start Button | 2020-06-05 | 2020-06-10 | 2020-06-09 | Parker | Button that closes the start menu window and starts the race program
7.3 |  | background | 2020-06-10 | 2020-06-18 | 2020-06-17 | Parker | something other than the void to make the start menu fun
7.4 |  | Credits Button | 2020-06-09 | 2020-06-10 | 2020-06-16 | Parker | Credits paying respect to our contributors
| *Separate Priority | Spec | 2020-02-13 | 2020-06-11 | n/a | Parker | Description of project and feature explaination
|  | WBS | 2020-02-13 | 2020-06-11 | n/a | Development | Features that are added / in development and who worked on them when
|  | Sprint Review | 2020-02-13 | 2020-06-11 | n/a | Parker | weekly check in to see progress on the game

## With Canceled
Priority | Feature Category | Feature | Assigned Date | Due Date | Completion Date | Assigned To | Decription
1 | Game World | Game World exists | No Record | 2020-02-13 | 2020-02-13 | Eli | A world that the player can view/interact with
6 |  | hills | Canceled | Canceled | Canceled |  | a raised portion of land on/off the track tht the player follows
18 |  | water | Canceled | Canceled | Canceled |  | ends level ?
17 |  | scenery | Canceled | Canceled | Canceled |  | foliage / level decoration
2 |  | Physics | No Record | 2020-02-27 | 2020-02-27 | Eli | gravity, drag, and collision (momentum / weight?)
4 |  | Terrain Mesh | No Record | 2020-02-13 | Canceled | Alex | terrain 3D texturing
3 | Player / Interaction | Driving | No Record | 2020-02-27 | 2020-02-27 | Eli | acceleration curve
8 |  | Complete HUD | 2020-05-06 | Canceled | Canceled | Mohammed | Interface for theplayer to monitor time, speed, and lap
9 |  | Pause Menu | 2020-06-10 | 2020-06-17 | Pending | Mohammed | interaction menu that the player triggers to stop car input in game
19 |  | Start Menu | 2020-06-05 | 2020-06-10 | 2020-06-09 | Parker | Basic menu for the player to start the game
11 | Obstacles | ice | Canceled | Canceled | Canceled | Parker | reduces friction between the car and ground slowing steering and speeding player up initialy but slowing over time
10 |  | 3D Obj Framework | 2020-05-24 | 2020-05-28 | 2020-05-25 | Parker | Framework for basic objects
10 |  | 3D Obj Framework 2 | 2020-06-03 | 2020-06-08 | Canceled | Parker | Framework for basic objects but again because it got yeeted
5 | Leveling | Second Level | 2020-04-27 | 2020-04-30 | Canceled | Kunal | second track for the player to drive on
12 |  | *Third Level | Canceled | Canceled | Canceled |  | third track for player to drive on
7 | Audio | engine noise | No Record | 2020-05-25 | Canceled | Sumedh | vroom vroom
13 |  | Background music (radio) | No Record | 2020-05-25 | Canceled | Eli & Sumedh | déjà vu
14 |  | start / finish sound | No Record | 2020-05-25 | Canceled | Sumedh | ding ding ding
18.1 |  | ambient water noise | No Record | 2020-05-25 | Canceled | Sumedh | splish splash
1 | Car Controls | Acceleration | 2020-02-27 | 2020-06-05 | 2020-06-04 | Eli | the rate at which the car increases speed to match the maximum
16 |  | E-brake | Pending | Pending | Pending |  | full stop all wheels rapid deceleration temporarily disable acceleration while pulled
2 |  | Steering | 2020-02-27 | 2020-06-06 | 2020-06-06 | Eli | car turns while moving forward ¦ A - turn left / D - turn right
15 |  | Boost | 2020-05-29 | 2020-06-05 | Pending | Kunal | a button pressed to temporarily increase speed
19.2 | Start Menu | Title Image | 2020-06-10 | 2020-06-18 | Pending | Alex | Image with the title of "Space Racer" and maybe icon if Alex is feeling charitable
19.1 |  | Start Button | 2020-06-05 | 2020-06-10 | 2020-06-09 | Parker | Button that closes the start menu window and starts the race program
19.3 |  | background | 2020-06-10 | 2020-06-18 | Pending | Mohammed | something other than the void to make the start menu fun
19.4 |  | Credits Button | 2020-06-09 | 2020-06-10 | Pending |  | Credits paying respects to our contributors
8.1 | HUD | Timer | 2020-05-07 | 2020-06-05 | Canceled | Mohammed | A timer showing the time the player has spent on a given round (Due date pushed 14 days)
8.2 |  | Map | Canceled | Canceled | Canceled | Mohammed | a smalll map in the coner of the screen showing the player their proggres through the track
15.1 |  | Boost Meter | Canceled | Canceled | Canceled | Mohammed | A circular meter that shows how full the players boost is
*1 | Documentation | Credits | 2020-02-13 | 2020-06-11 | n/a | Parker | List of people who contributed to the project
| *Separate Priority | Spec | 2020-02-13 | 2020-06-11 | n/a | Parker | Description of project and feature explaination
|  | WBS | 2020-02-13 | 2020-06-11 | n/a | Development | Features that are added / in development and who worked on them when
|  | Sprint Review | 2020-02-13 | 2020-06-11 | n/a | Parker | weekly check in to see progress on the game
|  | After Action Report | 2020-02-13 | 2020-06-18 | Pending | Parker & Kunal | After action report explaining development procces / what worked what didn't